## Revision History
Revision History
Date | Version | Description | Author
2016-10-05 | 0.1 | Initial Draft | Edi Prayitno
2016-10-10 | 1 | Update as Baseline document | Edi Prayitno

## Estimation
No | Type | Task Id | Task Description | Estimation (hours)
1 | Document | SCM001 | Compose SCM Plan | 2
2 | Document | SCM002 | Compose SRS | 2
3 | Document | SCM003 | Compose Test Plan | 2
4 | Document | SCM004 | Compsose Test Case | 2
5 | Document | SCM005 | Conduct Testing | 2
6 | Source Code | SCM006 | Develop Login/Logout user | 1
7 | Source Code | SCM007 | Develop Admin home page | 1
8 | Source Code | SCM008 | Develop Manage User | 1
9 | Source Code | SCM009 | Develop Manage Post | 1
10 | Source Code | SCM010 | Develop Home Page | 1
11 | Source Code | SCM011 | Develop View Post Page | 1
12 | Source Code | SCM012 | Cevelop SEO URLS Feature | 1
13 | Source Code | SCM013 | Develop Comment Feature | 1
14 | Source Code | SCM014 | Develop Category Feature | 1
15 | Source Code | SCM015 | Develop Sidebar Feature | 1
16 | Source Code | SCM016 | Develop Pagination Feature | 1